## Backlog
Epic ID | Epic | Story ID | User Story | Priority | Release | Owner Role | Acceptance Criteria | Dependencies | Status
E01 | Tenant & Customer Management | US-001 | As a Platform Admin, I need to create tenant so that the SOC platform can operate securely and repeatably. | High | MVP | Platform Admin | Create tenant is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E01 | Tenant & Customer Management | US-002 | As a Platform Admin, I need to configure service tier so that the SOC platform can operate securely and repeatably. | High | MVP | Platform Admin | Configure service tier is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E01 | Tenant & Customer Management | US-003 | As a Platform Admin, I need to manage escalation contacts so that the SOC platform can operate securely and repeatably. | High | MVP | Platform Admin | Manage escalation contacts is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E01 | Tenant & Customer Management | US-004 | As a Platform Admin, I need to track onboarding status so that the SOC platform can operate securely and repeatably. | High | MVP | Platform Admin | Track onboarding status is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E02 | Identity, RBAC & SSO | US-005 | As a Security Architect, I need to role-based permissions so that the SOC platform can operate securely and repeatably. | High | MVP | Security Architect | Role-based permissions is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E02 | Identity, RBAC & SSO | US-006 | As a Security Architect, I need to mfa enforcement so that the SOC platform can operate securely and repeatably. | High | MVP | Security Architect | MFA enforcement is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E02 | Identity, RBAC & SSO | US-007 | As a Security Architect, I need to sso support so that the SOC platform can operate securely and repeatably. | High | MVP | Security Architect | SSO support is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E02 | Identity, RBAC & SSO | US-008 | As a Security Architect, I need to privileged action audit so that the SOC platform can operate securely and repeatably. | High | MVP | Security Architect | Privileged action audit is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E03 | Ingestion & Normalisation | US-009 | As a Backend Engineer, I need to receive raw events so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Receive raw events is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E03 | Ingestion & Normalisation | US-010 | As a Backend Engineer, I need to normalize to common schema so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Normalize to common schema is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E03 | Ingestion & Normalisation | US-011 | As a Backend Engineer, I need to deduplicate events so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Deduplicate events is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E03 | Ingestion & Normalisation | US-012 | As a Backend Engineer, I need to create parser error queue so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Create parser error queue is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E04 | Alert Queue & Triage | US-013 | As a SOC Lead, I need to filter alert queue so that the SOC platform can operate securely and repeatably. | High | MVP | SOC Lead | Filter alert queue is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E04 | Alert Queue & Triage | US-014 | As a SOC Lead, I need to assign analyst so that the SOC platform can operate securely and repeatably. | High | MVP | SOC Lead | Assign analyst is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E04 | Alert Queue & Triage | US-015 | As a SOC Lead, I need to set severity/confidence so that the SOC platform can operate securely and repeatably. | High | MVP | SOC Lead | Set severity/confidence is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E04 | Alert Queue & Triage | US-016 | As a SOC Lead, I need to convert alert to incident so that the SOC platform can operate securely and repeatably. | High | MVP | SOC Lead | Convert alert to incident is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E05 | Incident Case Management | US-017 | As a Product Owner, I need to create incident case so that the SOC platform can operate securely and repeatably. | High | MVP | Product Owner | Create incident case is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E05 | Incident Case Management | US-018 | As a Product Owner, I need to build incident timeline so that the SOC platform can operate securely and repeatably. | High | MVP | Product Owner | Build incident timeline is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E05 | Incident Case Management | US-019 | As a Product Owner, I need to manage tasks/actions so that the SOC platform can operate securely and repeatably. | High | MVP | Product Owner | Manage tasks/actions is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E05 | Incident Case Management | US-020 | As a Product Owner, I need to close with report so that the SOC platform can operate securely and repeatably. | High | MVP | Product Owner | Close with report is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E06 | Evidence & Audit Trail | US-021 | As a Compliance Lead, I need to store evidence item so that the SOC platform can operate securely and repeatably. | High | MVP | Compliance Lead | Store evidence item is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E06 | Evidence & Audit Trail | US-022 | As a Compliance Lead, I need to hash evidence so that the SOC platform can operate securely and repeatably. | High | MVP | Compliance Lead | Hash evidence is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E06 | Evidence & Audit Trail | US-023 | As a Compliance Lead, I need to export audit trail so that the SOC platform can operate securely and repeatably. | High | MVP | Compliance Lead | Export audit trail is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E06 | Evidence & Audit Trail | US-024 | As a Compliance Lead, I need to apply retention policy so that the SOC platform can operate securely and repeatably. | High | MVP | Compliance Lead | Apply retention policy is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | Architecture sign-off | Not Started
E07 | Customer Portal & Reporting | US-025 | As a Frontend Engineer, I need to customer incident view so that the SOC platform can operate securely and repeatably. | High | MVP | Frontend Engineer | Customer incident view is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E07 | Customer Portal & Reporting | US-026 | As a Frontend Engineer, I need to monthly report generation so that the SOC platform can operate securely and repeatably. | High | MVP | Frontend Engineer | Monthly report generation is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E07 | Customer Portal & Reporting | US-027 | As a Frontend Engineer, I need to executive dashboard so that the SOC platform can operate securely and repeatably. | High | MVP | Frontend Engineer | Executive dashboard is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E07 | Customer Portal & Reporting | US-028 | As a Frontend Engineer, I need to customer approval workflow so that the SOC platform can operate securely and repeatably. | High | MVP | Frontend Engineer | Customer approval workflow is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E08 | Microsoft Integrations | US-029 | As a Integration Engineer, I need to m365 audit connector so that the SOC platform can operate securely and repeatably. | High | MVP | Integration Engineer | M365 audit connector is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E08 | Microsoft Integrations | US-030 | As a Integration Engineer, I need to entra sign-in connector so that the SOC platform can operate securely and repeatably. | High | MVP | Integration Engineer | Entra sign-in connector is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E08 | Microsoft Integrations | US-031 | As a Integration Engineer, I need to defender alert connector so that the SOC platform can operate securely and repeatably. | High | MVP | Integration Engineer | Defender alert connector is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E08 | Microsoft Integrations | US-032 | As a Integration Engineer, I need to connector health monitoring so that the SOC platform can operate securely and repeatably. | High | MVP | Integration Engineer | Connector health monitoring is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E09 | Syslog/Webhook/API Collectors | US-033 | As a Backend Engineer, I need to syslog listener so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Syslog listener is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E09 | Syslog/Webhook/API Collectors | US-034 | As a Backend Engineer, I need to webhook endpoint so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Webhook endpoint is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E09 | Syslog/Webhook/API Collectors | US-035 | As a Backend Engineer, I need to customer api ingestion so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Customer API ingestion is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E09 | Syslog/Webhook/API Collectors | US-036 | As a Backend Engineer, I need to source authentication so that the SOC platform can operate securely and repeatably. | High | MVP | Backend Engineer | Source authentication is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E10 | Detection Engineering Workspace | US-037 | As a Detection Engineer, I need to rule catalogue so that the SOC platform can operate securely and repeatably. | Medium | V1 | Detection Engineer | Rule catalogue is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E10 | Detection Engineering Workspace | US-038 | As a Detection Engineer, I need to sigma upload/validation so that the SOC platform can operate securely and repeatably. | Medium | V1 | Detection Engineer | Sigma upload/validation is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E10 | Detection Engineering Workspace | US-039 | As a Detection Engineer, I need to mitre mapping so that the SOC platform can operate securely and repeatably. | Medium | V1 | Detection Engineer | MITRE mapping is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E10 | Detection Engineering Workspace | US-040 | As a Detection Engineer, I need to rule testing workflow so that the SOC platform can operate securely and repeatably. | Medium | V1 | Detection Engineer | Rule testing workflow is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E11 | Threat Intelligence Enrichment | US-041 | As a Threat Intel Lead, I need to ioc enrichment so that the SOC platform can operate securely and repeatably. | Medium | V1 | Threat Intel Lead | IOC enrichment is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E11 | Threat Intelligence Enrichment | US-042 | As a Threat Intel Lead, I need to tlp marking so that the SOC platform can operate securely and repeatably. | Medium | V1 | Threat Intel Lead | TLP marking is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E11 | Threat Intelligence Enrichment | US-043 | As a Threat Intel Lead, I need to stix/taxii feed support so that the SOC platform can operate securely and repeatably. | Medium | V1 | Threat Intel Lead | STIX/TAXII feed support is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E11 | Threat Intelligence Enrichment | US-044 | As a Threat Intel Lead, I need to watchlist management so that the SOC platform can operate securely and repeatably. | Medium | V1 | Threat Intel Lead | Watchlist management is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E12 | SOAR Playbooks & Approvals | US-045 | As a SOC Lead, I need to playbook designer so that the SOC platform can operate securely and repeatably. | Medium | V1 | SOC Lead | Playbook designer is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E12 | SOAR Playbooks & Approvals | US-046 | As a SOC Lead, I need to approval gate so that the SOC platform can operate securely and repeatably. | Medium | V1 | SOC Lead | Approval gate is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E12 | SOAR Playbooks & Approvals | US-047 | As a SOC Lead, I need to action connector run so that the SOC platform can operate securely and repeatably. | Medium | V1 | SOC Lead | Action connector run is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E12 | SOAR Playbooks & Approvals | US-048 | As a SOC Lead, I need to playbook audit log so that the SOC platform can operate securely and repeatably. | Medium | V1 | SOC Lead | Playbook audit log is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E13 | AI SOC Assistant | US-049 | As a AI Engineer, I need to alert summarisation so that the SOC platform can operate securely and repeatably. | Medium | V1 | AI Engineer | Alert summarisation is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E13 | AI SOC Assistant | US-050 | As a AI Engineer, I need to investigation suggestions so that the SOC platform can operate securely and repeatably. | Medium | V1 | AI Engineer | Investigation suggestions is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E13 | AI SOC Assistant | US-051 | As a AI Engineer, I need to incident report draft so that the SOC platform can operate securely and repeatably. | Medium | V1 | AI Engineer | Incident report draft is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E13 | AI SOC Assistant | US-052 | As a AI Engineer, I need to ai guardrail logging so that the SOC platform can operate securely and repeatably. | Medium | V1 | AI Engineer | AI guardrail logging is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E14 | Connector Marketplace | US-053 | As a Integration Engineer, I need to connector configuration ui so that the SOC platform can operate securely and repeatably. | Medium | V1 | Integration Engineer | Connector configuration UI is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E14 | Connector Marketplace | US-054 | As a Integration Engineer, I need to credential vault integration so that the SOC platform can operate securely and repeatably. | Medium | V1 | Integration Engineer | Credential vault integration is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E14 | Connector Marketplace | US-055 | As a Integration Engineer, I need to rate-limit handling so that the SOC platform can operate securely and repeatably. | Medium | V1 | Integration Engineer | Rate-limit handling is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E14 | Connector Marketplace | US-056 | As a Integration Engineer, I need to connector sdk template so that the SOC platform can operate securely and repeatably. | Medium | V1 | Integration Engineer | Connector SDK template is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E15 | MSSP/White-label Mode | US-057 | As a Product Owner, I need to partner hierarchy so that the SOC platform can operate securely and repeatably. | Medium | V2 | Product Owner | Partner hierarchy is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E15 | MSSP/White-label Mode | US-058 | As a Product Owner, I need to white-label branding so that the SOC platform can operate securely and repeatably. | Medium | V2 | Product Owner | White-label branding is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E15 | MSSP/White-label Mode | US-059 | As a Product Owner, I need to partner billing view so that the SOC platform can operate securely and repeatably. | Medium | V2 | Product Owner | Partner billing view is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E15 | MSSP/White-label Mode | US-060 | As a Product Owner, I need to sub-customer management so that the SOC platform can operate securely and repeatably. | Medium | V2 | Product Owner | Sub-customer management is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E16 | Sovereign/Dedicated Deployment | US-061 | As a Cloud Architect, I need to deployment profile so that the SOC platform can operate securely and repeatably. | Medium | V2 | Cloud Architect | Deployment profile is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E16 | Sovereign/Dedicated Deployment | US-062 | As a Cloud Architect, I need to data residency controls so that the SOC platform can operate securely and repeatably. | Medium | V2 | Cloud Architect | Data residency controls is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E16 | Sovereign/Dedicated Deployment | US-063 | As a Cloud Architect, I need to dedicated instance pipeline so that the SOC platform can operate securely and repeatably. | Medium | V2 | Cloud Architect | Dedicated instance pipeline is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started
E16 | Sovereign/Dedicated Deployment | US-064 | As a Cloud Architect, I need to dr runbook so that the SOC platform can operate securely and repeatably. | Medium | V2 | Cloud Architect | DR runbook is available in the relevant portal/API, is tenant-scoped, logged in audit trail, covered by tests, and documented. | MVP foundation | Not Started

## Integration Roadmap
Priority | Integration | Category | Phase | Direction | Data/Action Scope | Auth Method | Notes
1 | Microsoft 365 | Productivity/Email | MVP | Read | Audit logs, mailbox indicators, risky email activity | OAuth / Graph API | High market coverage
2 | Entra ID | Identity | MVP | Read/Action | Sign-ins, users, MFA, token/session actions | OAuth / Graph API | Core identity telemetry
3 | Microsoft Defender | EDR/XDR | MVP | Read/Action | Alerts, device info, isolate device where authorised | OAuth/API | Strong first EDR path
4 | Syslog | Generic | MVP | Read | Firewall/router/server/appliance events | TLS/syslog certs | Broadest generic ingestion
5 | Webhook/API | Generic | MVP | Read | Customer alerts/events from any source | API key/OAuth/HMAC | Flexible onboarding
6 | Jira / ServiceNow | Ticketing | MVP/V1 | Read/Write | Create/update tickets, sync status | OAuth/API tokens | Enterprise workflow
7 | AWS | Cloud | V1 | Read | CloudTrail, GuardDuty, IAM, security findings | IAM role/API | Cloud expansion
8 | Azure | Cloud | V1 | Read | Activity logs, Defender for Cloud, security alerts | OAuth | Microsoft enterprise
9 | Fortinet | Firewall | V1 | Read/Action | Firewall logs, block IP/domain where authorised | API/syslog | Common network control
10 | Palo Alto | Firewall | V1 | Read/Action | Firewall/threat logs, policy block | API/syslog | Enterprise firewall
11 | CrowdStrike | EDR | V1 | Read/Action | Detections, host telemetry, isolate host | OAuth/API | Premium MDR
12 | SentinelOne | EDR | V1 | Read/Action | Threats, endpoint response actions | API token | Premium MDR
13 | Okta | Identity | V2 | Read/Action | Identity events, session/account actions | OAuth/API | Enterprise identity
14 | Cloudflare | Edge | V2 | Read/Action | WAF/DNS/access logs, blocklists | API token | Edge/cloud security
15 | Zscaler | SASE | V2 | Read/Action | Web/proxy/zero-trust events | API | Large enterprise
16 | Vulnerability scanners | Exposure | V1 | Read | Findings, asset criticality, remediation status | API | Exposure management

## Playbooks
Playbook | Initial Severity | Required Data | Automated Evidence | Possible Actions | Approval Required | Owner
Phishing / BEC | P2 | Email logs, identity logs, user/device data | Email headers, recipient list, clicked links, mailbox rules | Quarantine email, revoke sessions, reset password | Yes for account actions | SOC Lead
Compromised identity | P2 | Sign-in logs, MFA, admin changes | Recent sign-ins, MFA changes, token use, mailbox activity | Revoke sessions, disable account, reset password | Yes unless pre-authorised | Tier 2 Analyst
Malware endpoint | P2 | EDR telemetry, process tree, hash intel | Process tree, file hash, network connections, device owner | Isolate device, kill process, quarantine file | Yes | Tier 2 Analyst
Ransomware suspected | P1 | EDR, file activity, identity, network | Affected assets, file rename patterns, lateral movement, backup status | Isolate endpoints, block indicators, escalate IR | Emergency policy | IR Lead
Cloud account compromise | P2 | Cloud audit, IAM, network, workload logs | API calls, IAM changes, resource creation | Disable key, rotate credentials, block source | Yes | Cloud Security
Data exfiltration suspected | P1/P2 | Network, DLP, cloud storage, file access | Volume, destination, user/entity, sensitive asset link | Block destination, disable account, legal escalation | Yes | IR Lead

## Detection Use Cases
Domain | Use Case | Data Sources | MITRE Mapping | Default Severity | MVP/V1/V2 | Notes
Identity | Impossible travel followed by MFA change | Entra/Okta/Google | Initial Access / Credential Access | P2 | MVP | Validate user travel and VPN exceptions
Identity | Repeated MFA denied prompts | Entra/Okta | Credential Access | P2 | MVP | Potential MFA fatigue
Email | Mailbox forwarding rule to external address | M365/Google Workspace | Collection / Exfiltration | P2 | MVP | High BEC value
Email | Phishing click plus risky sign-in | Email security + identity | Initial Access | P2 | MVP | Correlated detection
Endpoint | Encoded PowerShell command | Defender/CrowdStrike/SentinelOne | Execution | P2/P3 | V1 | Tune admin scripts
Endpoint | Ransomware-like file modifications | EDR / file telemetry | Impact | P1/P2 | V1 | Critical containment
Cloud | Admin key created for privileged user | AWS/Azure/GCP | Privilege Escalation | P2 | V1 | Monitor service accounts
Network | Outbound to malicious IP/domain | Firewall/DNS/proxy | Command and Control | P2/P3 | V1 | Threat intel context
Vulnerability | Exploited critical vulnerability exposed to internet | Scanner + firewall + threat intel | Initial Access | P1/P2 | V1 | Tie to asset criticality
Data | Large unusual outbound transfer from critical system | Network/cloud/storage | Exfiltration | P1/P2 | V2 | Requires baseline

## Dashboard
SOC Platform Build Backlog Dashboard
Total user stories | 64
MVP user stories | 36
V1 user stories | 20
V2 user stories | 8
High priority stories | 36
Integration items | 16
Detection use cases | 10
Playbooks defined | 6